## Narasimhulu-User Stories
EPIC | User Stories
Instructor Module | As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Expected Time | Actual Time | Start Time | Task Status | End Time | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail) | User Story Point
| Instructor | Add a Question | A new question is added to Question Bank | Instructor should be logged in | All the values should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 | Narshimhulu |  | Given the Instructor wants to add the question to Question Bank he/she clicks on "Add Question" button then "Added question sucessfully" displays | Given the Instructor wants to add the question to Question Bank he/she clicks on "Add Question" button then "No message gets displayed" | 1
| Instructor | View Questionbank | Questions added to Question Bank can be seen | Instructor should be logged in | All Questions Should be present in DataBase | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Given the Instructor wants to see the Question Bank he/she clicks on "View All Questions" button then "List of Questions will be Displayed" | Given the Instructor wants to see the Question Bank he/she clicks on "View All Questions" button then "List of Questions will be Displayed" | 1
| Instructor | Update Question | Any Question In Question Bank can be modified | Instructor should be logged in | All the values should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Instructor wants to Update the Question Bank he/she clicks on "Update Question" button then "Question Updated Sucessfully" displays | Instructor wants to Update the Question Bank he/she clicks on "Update Question" button then "No Message will be displayed" | 1
| Instructor | Delete Question | An Question is deleted from Question Bank | Instructor should be logged in | Question Should Be Present in DataBase | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Instructor wants to Delete the Question from Question Bank he/she clicks on "Delete Question" button then "Question Deleted Sucessfully" displays | Instructor wants to Delete the Question from Question Bank he/she clicks on"Delete Question" then "No message will be diaplayed" | 1

## Amar-UserStories
EPIC | User Stories
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Expected Time | Actual Time | Start Time | Task Status | End Time | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail) | User Story Point
| Admin | Add a User | A new policy is added in the database | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 | Amar Upadhyaya | should have started working on ui but got busy with the yptool project | Given the Admin wants to add the User to the database he/she all the necessary details and clicks on "select user" button then "Choose a list of policies" click on "Add user" buttton then "User is added successfully Displays" | Given the Admin wants to add the user to database he/she all the necessary details and clicks on "select user" button then "Choose a list of polices" click on "Add user" buttton then "No message displays" | 1
| Admin | Update a User | Existing User can be updated with new Policies | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Given the Admin wants to update the existig User to the database he/she chooses the user from a list of user then neccesary details and click on "update user" button then "User is updated successfully Displays" | Given the admin wants to update a existing user he/she chooses the user from a list of user then fill all the necessary details and on "Update user Button" then "No message displays" | 1
| Admin | Deactivate a User | Deactivate a Existing User | Admin should be logged in | Admin Should choose a User From a list of user | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Given the Admin wants to deactivate the existing user he/she choose a user from alist of user then click on "Deactivate User " button then "User is successfully deactivated displays" | Given the Admin wants to deactivate the existing user he/she choose a user from alist of user then click on "Deactivate User " button then "No message Displays" | 1
| Admin | Assign Agent | Admin Can Assign a Agent to a Policyholder | Admin should be logged in | UserID Field should not be empty | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Admin wants to assign a agent to a policyholder he/she choose a policyholder with userID from list of agent and click on "Assign agent" Button then "Agent is successfully assigned displays" | Admin wants to assign a agent to a policyholder he/she choose a policyholder with userID from list of agent and click on "Assign Agent" Button then "No message displays" | 1
| Admin | Get Result | Admin can get Result of the agent for a policyholder | Admin should be logged in | UserID Field should not be empty | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Admin wants to get result of a agent he/she choose a agent with userID and click on "Get Result" Button then "Details gets Displayed" | Admin wants to get result of a agent he/she choose a agent with userID and click on "Get Result" Button then "No message Displays" | 1

## Puneet And Madhavi-UserStories
EPIC | User Stories
Candidate Module | As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Expected Time | Actual Time | Start Time | Task Status | End Time | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail) | User Story Point
| Candidate | Login | Test page will open | Login ID & Password is mandatory. | Values should not be NULL and filled correctly. | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.15h 29-01-2021 8.1h 29-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Given the candidate wants to login and he/she clicks on "Login" button then "Login Successfully" message displayed. | Given the candidate wants to login and he/she clicks on "Login" button then "Login Successfully" but no message displayed. | 1
| Candidate | Choose Test | To select the test details in order test series ection | Candidate should be logged in | Values should not be NULL and filled correctly. | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.15h 29-01-2021 8.1h 29-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  | Laptop is broken not able to complete front-end on time | Given the candidate wants to select the test and he/she clicks on "select test" button then the "test selected successfully" message displayed | Given the candidate wants to select the test and he/she clicks on "select test" and "test is not seleted" message is displayed | 1
| Candidate | Take Test | A new candidate is added to the Candidate Database | Candidate should be logged in | Values should not be NULL and filled correctly. | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.15h 29-01-2021 8.1h 29-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 | Puneet & Madhavi | Laptop is broken not able to complete front-end on time | Given the candidate wants to take test and he/she clicks on "Take Test" button then "test placed sucessfully" displays | Given the candidate wants to take the test of any given test series and he/she clicks on "Take Test" button then no message gets displayed | 1
| Candidate | View All Tests | A new candidate is added to the Candidate Database | Candidate should be logged in | Candidate should be authorised person. | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.15h 29-01-2021 8.1h 29-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  | Laptop is broken not able to complete front-end on time | Given the candidate wants to view all Tests and he/she clicks on "View All Tests" button then the detail of all Tests get displayed | Given the candidate wants to view all Tests and he/she clicks on "View All Tests" button and nothing is displayed | 1
| Candidate | View All Questions | A new candidate is added to the Candidate Database | Candidate should be logged in | Candidate should be authorised person. | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.15h 29-01-2021 8.1h 29-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  | Laptop is broken not able to complete front-end on time | Given the candidate wants to view all questions and he/she clicks on "View All" button then the detail of all quesitons get displayed | Given the candidate wants to view all questions and he/she clicks on "View All" button and nothing is displayed | 1
| Candidate | Submit | Candidate click on submit button after taking the test. | Candidate should be logged in | Candidate should be authorised person. | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.15h 29-01-2021 8.1h 29-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  | Laptop is broken not able to complete front-end on time | Given the candidate wants to submit the test and he/she clicks on "Submit" button then "Submit Test Successfully" message is displayed. | Given the candidate wants to submit all questions and he/she clicks on "Submit" button and nothing is displayed | 1
| Candidate | Logout | Candidate is logout after submit the test. | Candidate should be logged in | Candidate should be authorised person. | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.15h 29-01-2021 8.1h 29-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  | Laptop is broken not able to complete front-end on time | Given the candidate wants to Logout from the test and he/she clicks on "Logout" button then "Logout Successfully" message is displayed. | Given the candidate wants to Logout from the test and he/she clicks on "Logout" button and nothing is displayed | 1

## Bhoomika&TanuShree-UserStories
EPIC | User Stories
LOGIN MODULE | As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Expected Time | Actual Time | Start Time | Task Status | End Time | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail) | User Story Point
| User | Signup to portal page | user can access the benefits of portal | User should open an website | All the values should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 | Bhoomika & Tanusree |  | Given the user wants to signup and he/she clicks the signup button, enters all the details and then "profile successfully created" message displays | Given the user wants to signup and he/she clicks the signup button, enters all the details and then no message displays | 1
| User | Signin to user from login page | Student Examination page will open | User should be registered/signedup | All the values like login and password should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  | Travelling to Benguluru To Collect Cg laptop | Given the user wants to login and he/she clicks on "Login" button then "Login Successfully" message displayed. | Given the user wants to login and he/she clicks on "Login" button then no message is displayed. | 1
| Admin | Signin to admin from login page | Admin page will open | Admin details should be stored in database | Details like login and password should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Given the admin wants to login and he/she clicks on "Login" button then "Login Successfully" message displayed. | Given the admin wants to login and he/she clicks on "Login" button then no message displayed. | 1
| User | Update a profile | User can edit his/her profile details | User should be logged in | All fields should be filled correctly and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Given user wants to update a profile and he/she clicks the update profile button, enters all the details and then "profile successfully updated" message displays | Given user wants to update a profile and he/she clicks the update profile button, enters all the details and then no message displays | 1