## Narasimhulu-User Stories
EPIC | User Stories
Instructor Module | As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Expected Time | Actual Time | Start Time | Task Status | End Time | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail) | User Story Point
| Instructor | Add a Question | A new question is added to Question Bank | Instructor should be logged in | All the values should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 | Narshimhulu |  | Given the Instructor wants to add the question to Question Bank he/she clicks on "Add Question" button then "Added question sucessfully" displays | Given the Instructor wants to add the question to Question Bank he/she clicks on "Add Question" button then "No message gets displayed" | 1
| Instructor | View Questionbank | Questions added to Question Bank can be seen | Instructor should be logged in | All Questions Should be present in DataBase | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Given the Instructor wants to see the Question Bank he/she clicks on "View All Questions" button then "List of Questions will be Displayed" | Given the Instructor wants to see the Question Bank he/she clicks on "View All Questions" button then "List of Questions will be Displayed" | 1
| Instructor | Update Question | Any Question In Question Bank can be modified | Instructor should be logged in | All the values should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Instructor wants to Update the Question Bank he/she clicks on "Update Question" button then "Question Updated Sucessfully" displays | Instructor wants to Update the Question Bank he/she clicks on "Update Question" button then "No Message will be displayed" | 1
| Instructor | Delete Question | An Question is deleted from Question Bank | Instructor should be logged in | Question Should Be Present in DataBase | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h | 1.20m 14-01-2021 2.20m 15-01-2021 3.20m 18-01-2021 4.20m 19-01-2021 5.20m 20-01-2021 7.5h 21-01-2021 24-01-2021 8.1h 25-01-2021 | 2021-01-13 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done | 2021-01-27 |  |  | Instructor wants to Delete the Question from Question Bank he/she clicks on "Delete Question" button then "Question Deleted Sucessfully" displays | Instructor wants to Delete the Question from Question Bank he/she clicks on"Delete Question" then "No message will be diaplayed" | 1

## InsuranceUserStories
EPIC | User Stories
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Expected Time | Actual Time | Start Time | Task Status | End Time | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail) | User Story Point
| Admin | Add Agent | A new Agent is added in the database | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation 8.Integration | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Admin wants to add the Agent to the database he/she all the necessary details and clicks on "Select Agent" button then "Choose a list of users " click on "Add Agent" buttton then "Agent is added successfully Displays" | Given the Admin wants to add the Agent to database he/she all the necessary details and clicks on "select Agent" button then "Choose a list of users" click on "Add Agent " buttton then "No message displays" | 1
| Admin | Update Agent | Existing Agent is updated in the database | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Admin wants to update the existig Agent to the database he/she chooses the user from a list of Agent then neccesary details and click on "update Agent" button then "Agent is updated successfully Displays" | Given the admin wants to update a existing Agent he/she chooses the Agent from a list of Agent then fill all the necessary details and on "Update Agent Button" then "No message displays" | 1
| Admin | View Agent | Agent Information is displayed | Admin should be logged in | Admin Should choose a Agent from a list of Agent | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Admin wants to view Agent he/she choose a Agent from a list of Agent then click on "view Agent " button then "Agent Information displays" | Given the Admin wants to view Agent he/she choose a Agent from a list of Agent then click on "view Agent " button then "No message Displays" | 1
| Admin | Remove Agent | Agent is removed from database | Admin should be logged in | AdminID Field should not be empty | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Admin wants to remove Agent to a he/she choose a Agent with AgentID from list of agent and click on "Remove Agent" Button then "Agent is successfully removed displays" | Admin wants to remove a Agent he/she choose a Agent with AgentID from list of agent and click on "Remove Agent" Button then "No message displays" | 1
| Admin | Add Policy | New policy is added to database | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-30 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Admin wants to add policy he/she choose a policy with policyID and click on "Add Policy" Button then "Policy Added Successfully Displayed" | Admin wants to add policy he/she choose a policy with policyID and click on "Add Policy" Button then "No message Displays" | 1
| Admin | Update Policy | Existing policy is updated in the databse | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Admin wants to update policy to the database he/she chooses a policy from a list of policy then neccesary details and click on "update Policy" button then "Policy is updated successfully Displays" | Given the admin wants to update policy he/she chooses the policy from a list of policy then fill all the necessary details and on "Update Policy Button" then "No message displays"
| Admin | View Policy | Policies information is displayed | Admin should be logged in | Admin should be logged in | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creatio | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Admin wants to view policies he/she choose a policy from a list of Policy then click on "View Policy" button then "Policy Information displays" | Given the Admin wants to view policies he/she choose a policy from a list of Policy then click on "view policy " button then "No message Displays"
| Admin | Remove Policy | Policy is removed from the database | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Admin wants to remove policy to a he/she choose a policywith policyID from list of policies and click on "Remove Policy" Button then "Policy is successfully removed displays" | Admin wants to remove policy to a he/she choose a policywith policyID from list of policies and click on "Remove Policy" Button then "No message displays"
| Admin | View User | User information is displayed | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Admin wants to view user he/she choose a user from a list of User then click on "view User " button then "User Information displays" | Given the Admin wants to view user he/she choose a user from a list of User then click on "view User " button then "No message displays"
| Admin | Add Commission | Commision is added to databse | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Admin wants to add the commision to the database he/she all the necessary details and click on "Add Commission" buttton then "Commision is added successfully Displays" | Given the Admin wants to add the commision to the database he/she all the necessary details and click on "Add Commission" buttton then "No message Displays"
| Admin | View Commission | Commission is displayed | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creation | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Admin wants to view commission he/she choose a "View Commission" button then "Commission displays" | Given the Admin wants to view commission he/she choose a "View Commission" button then "No message Displays"
| Admin | Update Commission | Commision is updated to databse | Admin should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creatio | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Admin wants to update commission of agent to the database he/she chooses the commission then neccesary details and click on "update Commission" button then "Commision is updated successfully Displays" | Given the Admin wants to update commission of agent to the database he/she chooses the commission then neccesary details and click on "update Commission" button then "No message Displays"
| User | Buy Policy | Policy is added to user's database | User should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creatio | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the user want buy policy he/she chooses the policy from list of policies then click on "Buy Policy" button then "Policy Buyed Successfully" | Given the user want buy policy he/she chooses the policy from list of policies then click on "Buy Policy" button then "No message Dsiplays"
| User | Make Payment | Policy is added to user's database | User should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creatio | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the user want make payment he/she chooses the policy from list of policies then click on "Buy Policy" button then click on "Pay Premium" button then "Payment Successful" | Given the user want make payment he/she chooses the policy from list of policies then click on "Buy Policy" button then click on "Pay Premium" button then "No message Displays"
| Agent | View User and Policies | User and policies information is Displayed | Agent should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creatio | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Agent want to view User and Policies he/she chooses the user and policy from a list of user and policy the click on "View User" and "View Policy" button then "User Information" and "Policies" | Given the Agent want to view User and Policies he/she chooses the user and policy from a list of user and policy the click on "View User" and "View Policy" button then "No message Displays"
| Agent | View Commission | Commission is displayed | Agent should be logged in | All the details should be correctly filled and should not be null | 1.Creating Entity 2.Making repository and DAO layer. 3.Making Service layer 4.Making Controller layer 5.Exception Handling 6.Adding jUnit Testing 7.UI Creatio | 1.20m 2.20m 3.20m 4.20m 5.20m 6.20m 7.5h 8.1h |  | 2021-10-29 | 1.Done 2.Done 3.Done 4.Done 5.Done 6.WIP 7.Done 8.Done |  |  |  | Given the Agent wants to view commission he/she choose a "View Commission" button then "Commission displays" | Given the Agent wants to view commission he/she choose a "View Commission" button then "No message Displays"